Publication Roadmap 
From Idea to Publication
BOOK TITLE (TENTATIVE): Bella Makes Life
Name: Mary Brown

Actions and Deadlines – Start with the end in mind and work backwards
Ebook & Print Publication Release Timeline:      June 16, 2024   

Book Launch Timeline: ______???_____2024_______________

NB** Timelines are tentative. Change may come as needed.
	
Actions
	
Deadlines – Start and Finish

	
Book Writing 
	
February 2-28 

	
eBook Cover Design
[takes place while manuscript is being written]
[5-7 days first draft then revision]
	February 14

	
Book Description
[during writing or first round of editing]
	
February 14

	
Structural (Beta Readers)
Copyediting
[30 Days]
	
March 1-30

	Revision and rewriting
	March and April

	Book Formatting and Proofreading
	April – May

	Cover completion, cover design, corrections and upload
	June Upload



